Quot PSE — Contracts & Milestone Payment

End-to-End Process Flow — Start to Finish & Payment

Public Sector ERP · Nigeria IFMIS · Delta State Pilot
Module: contracts  |  Related: accounting, procurement, workflow

# 1. Does a Contract / IPC go through a GRN?

Short answer: No. A Goods Received Note (GRN) is a procurement artefact for goods-only purchase orders. Capital-works, consultancy, and services contracts that operate on physical progress (roads, buildings, maintenance, engineering studies) DO NOT pass through a GRN. Their evidence of delivery is the Engineer's Interim Payment Certificate (IPC).

Two parallel P2P rails exist in Quot PSE:

| Rail | Trigger | Evidence of delivery | Matching | Payment doc |
| --- | --- | --- | --- | --- |
| Procurement (goods) | Purchase Requisition → Purchase Order | Goods Received Note (GRN) | 3-way match: PO + GRN + Invoice | Payment Voucher |
| Contracts (works/services) | Contract award → Activate | Interim Payment Certificate (IPC) | 3-way match: Contract + IPC + Voucher-gross | Payment Voucher |

Key distinction The IPC is the works-equivalent of a GRN + invoice rolled into one. The certifying Engineer attests that work has physically been executed to the certified percentage, and the IPC itself becomes the claim on the treasury. Quot PSE enforces this separation via ALLOWED_IPC_TRANSITIONS in contracts/models/payment.py.

# 2. Contract Lifecycle (State Machine)

Every contract advances through seven states. Transitions are enforced by ALLOWED_CONTRACT_TRANSITIONS; any attempt to skip a state is rejected with a clear error code.

| # | State | Meaning | Unlocks |
| --- | --- | --- | --- |
| 1 | DRAFT | Awarded, not yet operational. | Edit; Activate |
| 2 | ACTIVATED | Contract number assigned, balance ledger materialised. | Mobilization advance; IPCs; Variations |
| 3 | IN_PROGRESS | Physical execution underway. | Periodic IPCs; Variations; Measurement Books |
| 4 | PRACTICAL_COMPLETION | Engineer has issued Practical Completion Certificate. | Release of first half of retention |
| 5 | DEFECTS_LIABILITY | Defects Liability Period (DLP) running. | Defect rectification; second half of retention still held |
| 6 | FINAL_COMPLETION | End of DLP; Final Completion Certificate issued. | Release of final retention |
| 7 | CLOSED | Terminal. All payments reconciled. | Audit only |

# 3. IPC Lifecycle (State Machine)

The Interim Payment Certificate is the payable unit for works contracts. Each IPC moves linearly through seven states and can never skip a stage. Rejections kick the IPC back to DRAFT for rework.

| # | IPC State | Actor | Action |
| --- | --- | --- | --- |
| 1 | DRAFT | Site Engineer / Contractor rep. | Prepare quantities, rates, measurement references. |
| 2 | SUBMITTED | Site Engineer | Submit to Certifier. Integrity hash is frozen. |
| 3 | CERTIFIER_REVIEWED | Project Engineer / Certifier | Cross-check against Measurement Book. Cannot be the same user as the submitter (SoD). |
| 4 | APPROVED | Procurement Officer / Approver | Financial approval. Cannot be the certifier (SoD). |
| 5 | VOUCHER_RAISED | Accounts Payable | Raise Payment Voucher in Treasury module. Three-way-match validated: voucher_gross == IPC.net_payable. |
| 6 | PAID | Treasury / Cashier | Mark paid. VAT and WHT recorded at this point (FIRS cash-basis). Accrual journal posted. |
| — | REJECTED | Any reviewer | Returns to DRAFT for rework with rejection_reason captured. |

Segregation of Duties (SoD) Enforced via contracts.services.sod.actor_can_bypass_sod. Default rule: Submitter ≠ Certifier ≠ Approver. Superusers and users with an explicit bypass permission may override, but the override is audit-logged.

# 4. Full Process Flow — Start to Finish

The numbered steps below are the real sequence executed by the services layer and observed end-to-end by scripts/e2e_contracts_workflow.py.

| 1 | Create Contract (DRAFT) Actor: Procurement Officer | POST /api/v1/contracts/contracts/. Required: title, reference, contract_type, procurement_method, vendor, MDA, NCoA code, appropriation, fiscal_year, original_sum, mobilization_rate (≤15%), retention_rate (typically 10%), signed_date, contract_start_date, contract_end_date, defects_liability_period_days. |
| --- | --- | --- |

| 2 | Define Milestone Schedule Actor: Project Engineer | Attach MilestoneSchedule rows: milestone_number, description, scheduled_value, percentage_weight, target_date. Sum of scheduled_value must ≤ original_sum. Milestones drive valuation of IPC line items. |
| --- | --- | --- |

| 3 | Activate Contract (ACTIVATED) Actor: MDA Head + Finance | POST /contracts/{id}/activate/. Generates official contract_number, materialises ContractBalance ledger (mob_advance, retention_held, certified_to_date, paid_to_date = 0), opens IPC and variation endpoints. |
| --- | --- | --- |

| 4 | (Optional) Mobilization Advance Actor: Accounts Payable | MobilizationService.raise_voucher → mark_paid. Advance = mobilization_rate × original_sum. Recovered pro-rata from each subsequent IPC's gross via mobilization_recovery_this_cert. |
| --- | --- | --- |

| 5 | Contract moves to IN_PROGRESS Actor: Project Engineer | Contract.transition_to(IN_PROGRESS). Triggered when first IPC is submitted or via explicit transition call. |
| --- | --- | --- |

| 6 | Prepare IPC (DRAFT) Actor: Site Engineer | Capture cumulative_work_done_to_date, previous_certified, variation_claims, ld_deduction. System computes: this_certificate_gross, retention_deduction_this_cert, mobilization_recovery_this_cert, net_payable. |
| --- | --- | --- |

| 7 | Submit IPC (DRAFT → SUBMITTED) Actor: Site Engineer | IPCService.submit_ipc. Integrity hash of line items is frozen; any subsequent edit must re-enter via REJECTED → DRAFT. |
| --- | --- | --- |

| 8 | Engineer Certifies (SUBMITTED → CERTIFIER_REVIEWED) Actor: Certifier (different user) | IPCService.certify. SoD guard blocks submitter from certifying. Measurement Book reference can be attached for defensibility. |
| --- | --- | --- |

| 9 | Financial Approval (CERTIFIER_REVIEWED → APPROVED) Actor: Approver (different user) | IPCService.approve. Control checks: cumulative_certified ≤ contract_ceiling; ceiling = original_sum + Σ(approved variations). |
| --- | --- | --- |

| 10 | Raise Payment Voucher (APPROVED → VOUCHER_RAISED) Actor: Accounts Payable | Create PaymentVoucherGov (voucher_number, payment_type, tsa_account, gross_amount, wht_amount, net_amount, narration). IPCService.raise_voucher performs the 3-way match: abs(voucher_gross - ipc.net_payable) ≤ COHERENCE_TOLERANCE, else ThreeWayMatchError. |
| --- | --- | --- |

| 11 | Mark Paid (VOUCHER_RAISED → PAID) Actor: Treasury / Cashier | IPCService.mark_paid(payment_date, vat_amount, wht_amount). Posts accrual journal; updates ContractBalance.cumulative_gross_paid; records FIRS tax liability (cash-basis). Retention is held; not paid to vendor. |
| --- | --- | --- |

| 12 | (If any) Variation Orders Actor: Engineer + Approver Tier | ContractVariation auto-computes approval_tier: LOCAL ≤15%, BOARD ≤25%, BPP_REQUIRED >25% of original_sum. Only APPROVED variations raise the ceiling. |
| --- | --- | --- |

| 13 | Practical Completion Actor: Engineer | Issue CompletionCertificate (PRACTICAL). Contract → PRACTICAL_COMPLETION. RetentionService releases the first half: raise_voucher → mark_paid. |
| --- | --- | --- |

| 14 | Defects Liability Period Actor: MDA + Vendor | Contract → DEFECTS_LIABILITY. Duration = contract.defects_liability_period_days. Defect rectifications are zero-value IPCs or variations. |
| --- | --- | --- |

| 15 | Final Completion Actor: Engineer | End of DLP + no outstanding defects. Final CompletionCertificate issued. Contract → FINAL_COMPLETION. |
| --- | --- | --- |

| 16 | Release Final Retention Actor: Accounts Payable + Treasury | RetentionService.raise_voucher → mark_paid on the remaining retention pool. ContractBalance.retention_held → 0. |
| --- | --- | --- |

| 17 | Close Contract Actor: Procurement Officer | POST /contracts/{id}/close/. Control checks: cumulative_gross_certified == cumulative_gross_paid + retention_released; no open IPCs; no pending variations. Contract → CLOSED (terminal). |
| --- | --- | --- |

# 5. Process-Flow Diagram (Text)

ASCII representation suitable for pasting into presentations or rendering to graphviz. Dashed edges are optional; solid edges are mandatory state transitions.

CONTRACT LIFECYCLE
------------------
   [Award]
      |
      v
  (DRAFT) --activate--> (ACTIVATED) --first IPC--> (IN_PROGRESS)
                             |                            |
                             |                            v
                             |               (PRACTICAL_COMPLETION)
                             |                            |
                             |                            v
                             |                 (DEFECTS_LIABILITY)
                             |                            |
                             |                            v
                             |                  (FINAL_COMPLETION)
                             |                            |
                             +---- retention & close -----+
                                          |
                                          v
                                      (CLOSED)

IPC LIFECYCLE (per payment period)
----------------------------------
  (DRAFT) --submit--> (SUBMITTED) --certify--> (CERTIFIER_REVIEWED)
      ^                   |                        |
      |                reject                   reject
      |                   v                        v
      +--- (REJECTED) <--+----- approve -----> (APPROVED)
                                                   |
                                            raise voucher
                                                   v
                                         (VOUCHER_RAISED)
                                                   |
                                                mark paid
                                                   v
                                                (PAID)

WORKS vs GOODS (Payment Evidence)
---------------------------------
  GOODS (procurement):    PR -> PO -> GRN -> Invoice -> 3-way-match -> PV -> Pay
  WORKS (contracts):      Contract -> Activate -> IPC (cert'd) ------> PV -> Pay
                                                   ^
                                                   +-- IPC replaces GRN+Invoice

# 6. Financial Controls & Computations

| Control | Where enforced | Formula / Rule |
| --- | --- | --- |
| Ceiling never breached | IPCService.approve, ContractVariation.save | Σ(certified) ≤ original_sum + Σ(approved variations). |
| Retention held on every IPC | IPCService._compute_deductions | retention_deduction_this_cert = this_certificate_gross × retention_rate%. |
| Mobilization recovery | MobilizationService.reconcile_payment_status | recovery_i = advance × (gross_i / original_sum) until fully recovered. |
| Three-way match | IPCService.raise_voucher | abs(voucher_gross − ipc.net_payable) ≤ COHERENCE_TOLERANCE else ThreeWayMatchError. |
| Variation tiered approval | ContractVariation.save (auto tier) | LOCAL ≤15%, BOARD (15–25%], BPP_REQUIRED >25% of original_sum. |
| Tax on payment | IPCService.mark_paid | VAT (7.5%) and WHT (typically 5% works) recorded at payment date (FIRS cash-basis). |
| SoD on IPC | contracts.services.sod | Submitter ≠ Certifier ≠ Approver unless bypass permission granted. |
| Integrity hash | InterimPaymentCertificate._compute_hash | SHA-256 of line-items frozen at submit; tamper detection on re-read. |

# 7. Worked Example — ₦10 M Road Contract

Following is the actual sequence exercised by the end-to-end harness (scripts/e2e_contracts_workflow.py) on contract E2E-001.

| Step | Amount | Running Certified | Running Paid | Retention Held |
| --- | --- | --- | --- | --- |
| Contract awarded (original_sum) | ₦10,000,000 | — | — | — |
| Contract activated | — | ₦0 | ₦0 | ₦0 |
| IPC #1 gross | ₦2,500,000 | ₦2,500,000 | — | ₦250,000 |
| IPC #1 paid (net) | ₦2,125,000 | ₦2,500,000 | ₦2,125,000 | ₦250,000 |
| IPC #2 gross | ₦2,500,000 | ₦5,000,000 | — | ₦500,000 |
| IPC #2 paid (net) | ₦2,125,000 | ₦5,000,000 | ₦4,250,000 | ₦500,000 |
| Variation #1 approved (ADDITION) | +₦1,000,000 | — | — | ceiling ↑ ₦11,000,000 |
| Practical Completion | — | ₦5,000,000 | ₦4,250,000 | ₦500,000 |
| Practical retention release | ₦250,000 | ₦5,000,000 | ₦4,500,000 | ₦250,000 |
| Final Completion | — | — | — | — |
| Final retention release | ₦250,000 | ₦5,000,000 | ₦4,750,000 | ₦0 |
| Contract CLOSED | — | ₦5,000,000 | ₦4,750,000 | ₦0 |

Net payable math (IPC #1) gross = 2,500,000 · retention (10%) = 250,000 · mob recovery (if any) = 0 this_certificate_net = 2,500,000 − 250,000 − 0 = 2,250,000 WHT at payment (5%) = 125,000 → bank pays contractor 2,125,000; FIRS receives 125,000.

# 8. Roles & Responsibilities (RACI)

| Activity | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Contract creation | Procurement Officer | MDA Head | Legal; Finance | Vendor |
| Activation | Procurement Officer | MDA Head | Finance | Vendor; AG |
| Mobilization payment | AP Officer | Accountant-General | Treasury | Vendor |
| IPC preparation | Site Engineer | Project Engineer | Contractor | — |
| IPC certification | Project Engineer | MDA Engineer | Measurement Book | AP |
| IPC approval | Finance Approver | MDA Head / PS | Internal Audit | Treasury |
| Voucher raising | AP Officer | Accountant-General | Treasury | Audit |
| Payment | Treasury / Cashier | Accountant-General | Bank; FIRS | Vendor |
| Variation approval | Tier actor | MDA / Board / BPP | Engineer | Vendor; AG |
| Retention release | AP + Treasury | Accountant-General | Engineer | Vendor |
| Closure | Procurement Officer | MDA Head | Audit | Vendor; AG |

# 9. API & Service Reference

| Step | HTTP Endpoint | Service call |
| --- | --- | --- |
| Create contract | POST /api/v1/contracts/contracts/ | ContractSerializer.create |
| Activate | POST /contracts/{id}/activate/ | ContractActivationService.activate |
| Create milestones | POST /api/v1/contracts/milestones/ | MilestoneSerializer.create |
| Transition state | POST /contracts/{id}/transition/ | Contract.transition_to |
| Raise mobilization | POST /contracts/{id}/mobilization/raise/ | MobilizationService.raise_voucher |
| Pay mobilization | POST /mobilization/{id}/pay/ | MobilizationService.mark_paid |
| Submit IPC | POST /ipcs/ | IPCService.submit_ipc |
| Certify IPC | POST /ipcs/{id}/certify/ | IPCService.certify |
| Approve IPC | POST /ipcs/{id}/approve/ | IPCService.approve |
| Raise voucher | POST /ipcs/{id}/raise-voucher/ | IPCService.raise_voucher |
| Mark paid | POST /ipcs/{id}/mark-paid/ | IPCService.mark_paid |
| Submit variation | POST /variations/ | ContractVariation.save |
| Approve variation | POST /variations/{id}/approve/ | VariationService.approve |
| Request retention release | POST /retentions/ | RetentionService.request |
| Pay retention | POST /retentions/{id}/pay/ | RetentionService.mark_paid |
| Close contract | POST /contracts/{id}/close/ | Contract.transition_to(CLOSED) |

Quot PSE · Nigeria IFMIS · Delta State pilot — process derived directly from contracts/, accounting/, and workflow/ source.